WORK-PLAN LOW VISION STEERING GROUP

| Session Number | Item | Action Required | Situation | Target | Responsibility |
| --- | --- | --- | --- | --- | --- |
| 1 | TORS | Draft, pass thru V2020UK + LVSIG | Complete | August 05 | LC |
| 2 | Outcomes Chart | Draft and agree with LVSG Inform V2020UK Incorporate in Business Plan | May be changed by LVSG as funding criteria demands | Done Nov 05 | LC/DSR |
| 3 | Review website | Create simple uncomplicated low cost site add hyperlinks Post minutes on site Setup automatic change of date facility & a counter | Andrew Bairstow will provide web management | Done Jan 06 | AB/MaryB/POW |
| 4 | Management Database | Task to be transferred to VISION 2020 UK | Database reviewed and to remain unchanged Set date for transfer | ASAP | MB |
| 5 | Draft Business Plan | Completed | Accepted by VISION 2020 UK Executive Committee | December 05 | LC LVSG |
| 6 | Job Specification(s) LV Implementation Officers/recruitment | Finalise Job specifications Draft structure chart Recruit LVIO – low cost Confirm funding V2020 members | Approved by VISION 2020 UK - further amendments to be done: first year funding agreed Amend as per V2020UK comments | ASAP | LC/MikeB |
| 7 | Sub Committees | Reaffirm purpose of sub committees and expected outcomes | Clear remit for Childrens and BME. Need guidance for Learning Disabilities Cttee & review membership | May 06 | LVSG DSR |
| 8 | Fundraising | Set out a time-table of action and responsibilities Application to VICTA Develop strategy to approach medium and low level funders | The Big Lottery – Programmes now available Garfield Weston and Comic Relief prove negative, await Johnson & Johnson response | TBD | LVSG MikeB |
| 9 | PR - LVSG | Draft Plan of forthcoming conferences and events Statement about the work of the Project Address Commissioning issues: invite a commissioning manager to attend LVSG? New Beacon Article to be published Purchase an easy to erect display stand. LC to get quotes | TBD Done - April 2006 Done - April 2006 | May 06 ASAP May 06 April 06 April 06 | DSR/Mary B LC/MaryB MaryB/PO’N LC LC |
| 10 | Governance | Decide: Composition of the LVSG Turnaround of Chair Review composition of Consultation Forum. | Done Done: LC in chair 2007 TBD | Nov 05 Jan 06 May 06 | LVSG LVSG LVSG |
| 11 | Low Vision Committees | More communication to LVSC Chairs of what is happening in other areas Develop User Guidance Induction Pack – theme for Chairs Conference | TBD TBD – agree Conference date etc | May 06 | Mary B MaryB/LC |