WORK-PLAN LOW VISION STEERING GROUP

8 September 2006

| Session Number | Item | Action Required | Situation | Target | Responsibility |
| --- | --- | --- | --- | --- | --- |
| 1 | TORS | Draft, pass thru V2020UK + LVSIG | Complete | August 05 | LC |
| 2 | Outcomes Chart | Draft and agree with LVSG Inform V2020UK Draft outcomes for Project for end of Year 1 as post Conference Report | May be changed by LVSG as funding criteria demands | Done Nov 05 Dec 06 | LC/DSR LC/ALL |
| 3 | Management Database | Task to be transferred to VISION 2020 UK | Database reviewed and to remain unchanged Transfer yet to be done | ASAP | MB MB/Mary B |
| 4 | Fundraising | Set out a time-table of action and responsibilities Application to VICTA - part support for Childrens post or Childrens Conference Develop strategy to approach medium and low level fund Arrange meeting with Lions representative | Big Lottery application – Submitted | Process ongoing Ongoing Ongoing | LVSG MikeB Mike B LC/TB |
| 5 | PR - LVSG | Draft Plan of forthcoming conferences and events Statement about the work of the Project Investigate purchase of banner for display stand – suitable for V 2020UK & RNIB Discuss sharing arrangements for PR Discussion on Campaigning issues | TBD ???? TBD TBD | ASAP Nov 06 Nov 06 | DSR/Mary B LC/MaryB Mary B TB/MB/AL LVSG |
| 6 | Governance | Annual re election of Chair Role of Consultation Forum – contact members re reporting routes via LVSG & V 2020 UK Check Position re rep from Soc Care Assoc. | On going TBD TBD | Nov 06 ASAP | LVSG LC/LVSG LC |
| 7 | Sub Committees | Reaffirm purpose of sub committees and expected outcomes | Look at need for LD Sub Group for V 2020UK | Nov 06 | MB/Mary B/ DSR |
| 8 | Low Vision Committees | More communication to LVSC Chairs of what is happening in other areas Develop User Guidance Induction Pack – theme for Chairs Conference Arrange Conference with forum for Chairs Seek help with administration After Conference – decide how best to support LVCs in promoting standards | TBD ????? Date fixed – 3 Nov | May 06 Nov 06 Feb O7 | Mary B MaryB/LC Mary B Mary B LVSG |