WORK-PLAN LOW VISION STEERING GROUP

| Session Number | Item | Action Required | Situation | Target | Responsibility |
| --- | --- | --- | --- | --- | --- |
| 1 | TORS | - Draft, pass thru V2020UK + LVSIG | Complete | August 05 | LC |
| 2 | Outcomes Chart | - Draft and agree with LVSG - Inform V2020UK - Incorporate in Business Plan | May be changed by LVSG as funding criteria demands | Done Nov 05 | LC/DSR |
| 3 | Review website | - Create simple uncomplicated low cost site add hyperlinks - Setup automatic change of date facility - Post minutes on site with workplan as separate document with link - Register domaine name - Establish costs of maintenance and registration and investigate sponsorship | Andrew Bairstow will provide web management | Done Jan 06 | AB/MaryB/POW |
| 4 | Management Database | - Task to be transferred to VISION 2020 UK | - Database reviewed and to remain unchanged - Set date for transfer | ASAP | MB |
| 5 | Draft Business Plan | Completed | Accepted by VISION 2020 UK Executive Committee | December 05 | LC LVSG |
| 6 | Job Specification(s) LV Implementation Officers/recruitment | - Finalise Job specifications - Draft structure chart - Recruit LVIO – low cost - Confirm funding V2020 members | - Approved by VISION 2020 UK - further amendments to be done: first year funding agreed - Amend as per V2020UK comments | ASAP | LC/MikeB |
| 7 | Sub Committees | - Reaffirm purpose of sub committees and expected outcomes | Clear remit for Childrens and BME. Need guidance for Learning Disabilities Cttee & review membership | May 06 | LVSG DSR |
| 8 | Fundraising | - Set out a time-table of action and responsibilities - Application to VICTA - Develop strategy to approach medium and low level fund | - The Big Lottery – Programmes now available - Garfield Weston and Comic Relief prove negative, await Johnson & Johnson response | TBD | LVSG MikeB |
| 9 | PR - LVSG | - Draft Plan of forthcoming conferences and events - Statement about the work of the Project - Address Commissioning issues: invite a commissioning manager to attend LVSG - New Beacon Article to be published - Purchase an easy to erect display stand. LC to get quotes | TBD Done – April 2006 Done – April 2006 | May 06 ASAP May 06 April 2006 April 2006 | DSR/Mary B LC/MaryB MaryB/PO’N LC LC |
| 10 | Governance | Decide: - Composition of the LVSG - Turnaround of Chair - Review composition of Consultation Forum. | Done Done: LC in chair 2007 TBD | Nov 05 Jan 06 May 06 | LVSG LVSG LVSG |
| 11 | Low Vision Committees | - More communication to LVSC Chairs of what is happening in other areas - Develop User Guidance Induction Pack – theme for Chairs Conference - Arrange Conference with forum for Chairs - Look at costs from previous event at QAC - Seek help with administration | TBD TBD – agree Conference date etc | May 06 | Mary B MaryB/LC |