WORK-PLAN LOW VISION STEERING GROUP

| Session Number | Item | Action Required | Situation | Target | Responsibility |
| --- | --- | --- | --- | --- | --- |
| 1 | TORS | Draft, pass thru V2020UK + LVSIG | Complete | August 05 | LC |
| 2 | Outcomes Chart | Draft and agree with LVSG Inform V2020UK Incorporate in Business Plan | May be changed by LVSG as funding criteria demands | Done Nov 05 | LC/DSR |
| 3 | Review website | Create simple uncomplicated low cost site add hyperlinks Setup automatic change of date facility Post minutes on site with workplan as separate document with link Register domaine name Establish costs of maintenance and registration and investigate sponsorship | Andrew Bairstow will provide web management | Done Jan 06 | AB/MaryB/POW |
| 4 | Management Database | Task to be transferred to VISION 2020 UK | Database reviewed and to remain unchanged Set date for transfer | ASAP | MB |
| 5 | Draft Business Plan | Completed | Accepted by VISION 2020 UK Executive Committee | December 05 | LC LVSG |
| 6 | Job Specification(s) LV Implementation Officers/recruitment | Finalise Job specifications Draft structure chart Recruit LVIO – low cost Confirm funding V2020 members | Approved by VISION 2020 UK - further amendments to be done: first year funding agreed Amend as per V2020UK comments | ASAP | LC/MikeB |
| 7 | Sub Committees | Reaffirm purpose of sub committees and expected outcomes | Clear remit for Childrens and BME. Need guidance for Learning Disabilities Cttee & review membership | May 06 | LVSG DSR |
| 8 | Fundraising | Set out a time-table of action and responsibilities Application to VICTA Develop strategy to approach medium and low level fund | The Big Lottery – Programmes now available Garfield Weston and Comic Relief prove negative, await Johnson & Johnson response | TBD | LVSG MikeB |
| 9 | PR - LVSG | Draft Plan of forthcoming conferences and events Statement about the work of the Project Address Commissioning issues: invite a commissioning manager to attend LVSG New Beacon Article to be published Purchase an easy to erect display stand. LC to get quotes | TBD Done – April 2006 Done – April 2006 | May 06 ASAP May 06 April 2006 April 2006 | DSR/Mary B LC/MaryB MaryB/PO’N LC LC |
| 10 | Governance | Decide: Composition of the LVSG Turnaround of Chair Review composition of Consultation Forum. | Done Done: LC in chair 2007 TBD | Nov 05 Jan 06 May 06 | LVSG LVSG LVSG |
| 11 | Low Vision Committees | More communication to LVSC Chairs of what is happening in other areas Develop User Guidance Induction Pack – theme for Chairs Conference Arrange Conference with forum for Chairs Look at costs from previous event at QAC Seek help with administration | TBD TBD – agree Conference date etc | May 06 | Mary B MaryB/LC |